## Fix and bugs
Test And Fix Bug — UAT Round 1 Bug Tracker
Z_BUG_WORKSPACE_MP v5.0 ¦ SAP S40 Client 324 ¦ Phase: SIT/UAT Round 1 ¦ Date: 17/04/2026
Document Information
Project Name | Z_BUG_WORKSPACE_MP — Bug Tracking System
Test Phase | SIT + UAT Round 1
Total Bugs Logged | 11
Version | 1.0
Date | 17/04/2026
Source | UAT Round 1 testing on S40 Client 324
Severity Classification
Severity | Description | SLA
CRITICAL | Short dump / system crash — blocks all testing | [6 empty] | Fix before re-test
High | Functional defect — incorrect behavior, data loss risk | [6 empty] | Fix before UAT Round 2
Medium | UX/design issue — workaround exists | [6 empty] | Fix before go-live
Low | Minor cosmetic issue | [6 empty] | Post go-live
Bug Tracker — UAT Round 1 (13/04/2026)
No. | Bug Title | Reproduction Steps | Expected Result | Actual Result | Root Cause | Fix Applied | Evidence | Severity | Status
1 | Short dump on tab Description/Dev Note/Tester Note | 1. Open BUG0000023 in Change mode (Screen 0300) 2. Click tab Description or Dev Note or Tester Note 3. ABAP short dump immediately | Tab opens, text editor displays existing content | CALL_FUNCTION_CONFLICT_TYPE short dump. Program terminates. | Custom Controls CC_DESC/CC_DEVNOTE/CC_TSTRNOTE not created on screens 0320/0330/0340 in SE51; or STRING field placed on screen layout causing deep type crash | CODE_PBO: Add TRY-CATCH around CREATE OBJECT go_cont_desc. CODE_F02: Explicit type cast lv_tdname TYPE tdobname before READ_TEXT. SE51: Verify CC_DESC on 0320, CC_DEVNOTE on 0330, CC_TSTRNOTE on 0340. | runtime-error-read-text-type-conflict-115802.png | CRITICAL | Fixed in v5.0
2 | Description text area too small — no dedicated full-screen view | User creates or views a bug. Description field appears in Bug Info area only. | Dedicated full Description tab with large text editor (CC_DESC) | Full editor (Screen 0320) not visible because tab crashes (Bug 1). | Root cause = Bug 1 tab crash | Fix Bug 1 -> full editor on tab Description (subscreen 0320) becomes accessible. | — | Medium | Resolved by Bug 1 fix
3 | Description field character limit | User types long description (>132 chars) in Description input area — text is cut off | Unlimited text (TYPE STRING) | Limited to ~132 visible characters | STRING field GS_BUG_DETAIL-DESC_TEXT placed directly on screen layout -> screen field limits visible length | Remove GS_BUG_DETAIL-DESC_TEXT from screen 0310 layout. Description stored only through cl_gui_textedit (CC_DESC_MINI). | — | Medium | Fixed in v5.0
4 | SAP Module, Severity, Created Date fields display empty | Open Display Bug for BUG0000023 (Screen 0310). SAP Module, Severity, Created Date all show blank. | Fields display correct values from ZBUG_TRACKER | Fields appear empty | Screen 0310 fields not mapped to correct global variables GS_BUG_DETAIL-SAP_MODULE, SEVERITY, CREATED_AT; or fields not added to screen layout in SE51 | Verify SE51 Screen 0310 field references. Add missing fields to layout. Check SE16 data for BUG0000023. | display-bug-bug0023-empty-metadata.png | High | Fix in SE51 screen 0310
5 | Remove User deletes row without selection | In Project Detail Screen 0500, press Remove User without clicking any row. User is deleted anyway. | Message: Please select a user row to remove. No deletion occurs. | Row is silently removed (default current_line used) | tc_users-current_line always has a value when TC has data. IF lv_line = 0 check insufficient. | Replace with GET CURSOR LINE lv_line and validate lv_line > 0 AND lv_line <= lines(gt_user_project) | change-project-remove-user-confirm.png | Medium | Fixed in v5.0 CODE_F01
6a | Create Bug: Status field allows non-New value | On Screen 0310 Create mode, open STATUS F4 help -> select status 3 (In Progress) -> save. Bug saved with status 3. | Status must always be 1 (New) when creating a bug | Status accepts any value from F4 | IF gs_bug_detail-status IS INITIAL guard bypassed when user explicitly selects via F4 | Force gs_bug_detail-status = gc_st_new unconditionally in save_bug. Lock STATUS field (screen group STS) in Create mode PBO. | create-bug-bug-info-status-3-no-upload.png | High | Fixed in v5.0 CODE_F01 + CODE_PBO
6b | Create Bug: SAP Module has no F4 search help | On Screen 0310, click SAP Module field -> no F4 help popup | F4 popup shows list: FI, MM, SD, ABAP, BASIS, PP, HR, QM | No search help appears; field is free-text only | Missing f4_sap_module FORM and POV module for SAP_MODULE field | Add FORM f4_sap_module in CODE_F02 using F4IF_INT_TABLE_VALUE_REQUEST. Add POV module f4_bug_sapmodule in CODE_PAI. | — | High | Fixed in v5.0 CODE_F02 + CODE_PAI
6c | Create Bug: Cannot upload evidence before bug is saved | On Screen 0310 Create mode, button UP_FILE (Upload Evidence) is hidden/disabled | UP_FILE available in Create mode — auto-saves bug first, then uploads | UP_FILE button not visible in Create mode | UP_FILE excluded from Create mode exclusion list in PBO | Remove UP_FILE from Create mode exclusion list. In upload_evidence, auto-call save_bug when gv_current_bug_id IS INITIAL AND gv_mode = gc_mode_create. | — | High | Fixed in v5.0 CODE_PBO + CODE_F01
6d | Create Bug: Created Date field shows empty before save | On Screen 0310 Create mode, CREATED_AT field shows blank | Created Date auto-populated with today date immediately | Field blank until save is triggered | CREATED_AT only set inside save_bug (post-save). PBO Create mode does not pre-fill. | PBO Create mode: add gs_bug_detail-created_at = sy-datum and gs_bug_detail-created_time = sy-uzeit. | — | Medium | Fixed in v5.0 CODE_PBO
7 | All screen fields lock after validation error | On Screen 0310, enter invalid data -> press Save -> validation error triggers -> ALL fields become locked | Error message in status bar, fields remain editable for correction | All screen fields locked, user cannot correct input | MESSAGE TYPE E in Module Pool locks screen fields for all non-grouped elements | Replace all MESSAGE TYPE E in save_bug_detail and save_project_detail with MESSAGE TYPE S DISPLAY LIKE E followed by RETURN | create-bug-validation-error-footer.png | High | Fixed in v5.0 CODE_F01
8 | Description text disappears in Display/Change mode | Open existing bug in Display mode (Screen 0300) -> Bug Info tab -> mini Description area is empty | Mini editor shows the bug description text | Mini editor blank even when description was saved | Description saved to Long Text Object (SAVE_TEXT) but not synced back to gs_bug_detail-desc_text DB field. Load re-reads DB field -> gets old/empty value. | After save_long_text, sync back: read go_edit_desc text -> concatenate lines -> assign to gs_bug_detail-desc_text -> update DB | — | High | Fixed in v5.0 CODE_F01
9 | Short dump CALL_FUNCTION_CONFLICT_TYPE in Change Bug | Screen 0300 -> Change -> tab click -> short dump (same as Bug 1 but confirmed on Change path) | Same as Bug 1 | CALL_FUNCTION_CONFLICT_TYPE short dump | Same root cause as Bug 1 | Same fix as Bug 1 | runtime-error-read-text-type-conflict-123322.png | CRITICAL | Fixed in v5.0 (same as Bug 1)
10 | Manager can set status backward (3 -> 1) without warning | Bug BUG0000024 status = 3 (In Progress). Manager opens Change -> changes status to 1 (New) -> saves. No warning. | Transition 3->1 should be blocked. Status must follow allowed transition matrix. | Status saved as 1 (New). System allows illegal backward transition. | Manager role case in change_bug_status appends ALL statuses to lt_allowed — no backward transition check | v5.0 redesign: Remove Manager bypass. Manager must follow transition matrix. Popup Screen 0370 only shows allowed next states. | change-bug-bug0024-status-in-progress.png + change-bug-bug0024-status-1-new-saved.png | CRITICAL | Fixed in v5.0 CODE_F01 (validate_transition)
11 | Status transition to Fixed (5) allowed without evidence | Bug BUG0000024 -> Change Status -> select Fixed (5) -> confirm -> saved without uploading any evidence file | Transition to Fixed (5) requires at least 1 evidence file in ZBUG_EVIDENCE | Status saved as Fixed with no evidence | check_evidence_for_status logic bypassed by Manager role (IF sy-subrc <> 0 AND gv_role <> M) | Remove Manager bypass in check_evidence_for_status. Popup Screen 0370 enforces evidence upload. ZBUG_EVIDENCE COUNT check applies to all roles. | change-bug-bug0024-status-5-fixed-saved.png | High | Fixed in v5.0 CODE_F01
Bug Statistics
Severity | Count | Fixed in v5.0 | Pending
CRITICAL | 3 (Bugs 1, 9, 10) | 3 | 0
High | 7 | 7 | 0
Medium | 4 (Bugs 2, 3, 5, 6d) | 4 | 0
Total | 11 | 11 | 0

## Issue 2
Files Changed in v5.0 Bug Fixes
SAP Include | Code Reference | Bugs Fixed | Change Description
Z_BUG_WS_TOP | CODE_TOP | 10, 11 | Add gc_st_finaltesting = 6, gc_st_resolved = V, screen group STS
Z_BUG_WS_PBO | CODE_PBO | 1, 6a, 6c, 6d, 9 | TRY-CATCH for container creation; lock STATUS (group STS); UP_FILE in Create mode; pre-fill CREATED_AT
Z_BUG_WS_PAI | CODE_PAI | 6b | Add POV module f4_bug_sapmodule
Z_BUG_WS_F01 | CODE_F01 | 5, 7, 8, 10, 11 | Fix remove_user_from_project cursor check; replace MESSAGE TYPE E with TYPE S DISPLAY LIKE E; sync desc_text after save_long_text; enforce transition matrix for Manager; remove Manager bypass in evidence check
Z_BUG_WS_F02 | CODE_F02 | 1, 6b, 9 | Explicit type cast lv_tdname TYPE tdobname before READ_TEXT; add f4_sap_module FORM
Screens to Verify in SE51
Screen | Action Required | Bugs Addressed
0310 | Remove STRING fields from layout; add SAP_MODULE, SEVERITY, CREATED_AT; add STATUS to group STS; add POV for SAP_MODULE |  | 3, 4, 6a, 6b, 6d
0320 | Verify Custom Control CC_DESC exists |  | 1, 2, 9
0330 | Verify Custom Control CC_DEVNOTE exists (no underscore) |  | 1, 9
0340 | Verify Custom Control CC_TSTRNOTE exists (no underscore) |  | 1, 9

## Issue 4
UAT Round 2 — Regression Plan
Re-test Item | Bug Ref | Test Account | Pass/Fail | Date | Notes
Open Change Bug -> tab Description/Dev Note/Tester Note | 1, 9 | DEV-089
Description full editor shows content | 2, 3, 8 | DEV-089
SAP Module, Severity, Created Date visible on Bug Info | 4 | DEV-089
Remove User requires row selection | 5 | DEV-089
Create Bug -> status forced to New | 6a | DEV-089
Create Bug -> SAP Module F4 shows list | 6b | DEV-089
Create Bug -> UP_FILE button visible + auto-saves bug | 6c | DEV-089
Create Bug -> Created Date pre-filled | 6d | DEV-089
Validation error -> fields remain editable | 7 | DEV-089
Manager cannot set status backward | 10 | DEV-089
Fixed requires evidence upload | 11 | DEV-089
Issue Category Breakdown
Category | Bugs | Description
A: Screen Layout / SE51 Issues | 1, 2, 3, 4, 9 | All require SE51 screen layout verification and correction.
B: Business Logic (ABAP Code) | 5, 7, 8, 10, 11 | Fixed in CODE_F01 v5.0.
C: Missing Features (Field / F4 Help) | 6a, 6b, 6c, 6d | Missing validations and helpers added in CODE_PAI + CODE_F02 v5.0.