## Sheet1
TR Management — Z_BUG_WORKSPACE_MP v5.0
SAP System: S40 ¦ Client: 324 ¦ Package: ZBUGTRACK ¦ Date: 17/04/2026
DOCUMENT INFORMATION
Project Name | Z_BUG_WORKSPACE_MP — Bug Tracking System
Transport Phase | v5.0 Deployment (UAT -> PRD)
SAP System | S40 Client 324
Package | ZBUGTRACK
Version | 1.0
Date | 17/04/2026
TR TYPE REFERENCE
Type | Description
Workbench | ABAP code, screens, GUI statuses, Data Dictionary objects (SE38, SE51, SE41, SE11, SE93)
Customizing | SPRO configuration (not applicable for this project — custom ABAP only)
TRANSPORT REQUEST LOG
No. | Owner | Account | Type | TR Number | Prerequisite TR | Description | Import By (UAT) | Release Date (UAT) | Import By (PRD) | Release Date (PRD)
TR-01 | DEV-089 | DEV-089 | Workbench | S40K9000001 | — | DB: ZBUG_EVIDENCE table — Create table ZBUG_EVIDENCE (11 fields: BUG_ID, EVIDENCE_ID, FILE_NAME, FILE_TYPE, FILE_SIZE, UPLOADED_BY, UPLOADED_AT, CONTENT TYPE RAWSTRING, DESCRIPTION, PROJECT_ID, EVIDENCE_TYPE). Package ZBUGTRACK. | DEV-089 |  | DEV-089
TR-02 | DEV-089 | DEV-089 | Workbench | S40K9000002 | TR-01 | DB: ZBUG_TRACKER extension — Add 13 new fields: SAP_MODULE (CHAR20), BUG_TYPE, PRIORITY, SEVERITY, DEVELOPER_ID, TESTER_ID, FIXED_DATE, TESTED_DATE, TRANS_NOTE (STRING), CREATED_TIME, UPDATED_TIME + missing Data Elements/Domains. | DEV-089 |  | DEV-089
TR-03 | DEV-089 | DEV-089 | Workbench | S40K9000003 | TR-02 | DB: ZBUG_PROJECT table — Create table (16 fields: PROJECT_ID, PROJECT_NAME, DESCRIPTION, STATUS, MANAGER_ID, CREATED_BY, CREATED_AT, CREATED_TIME, UPDATED_BY, UPDATED_AT, UPDATED_TIME, PRIORITY, CATEGORY, START_DATE, END_DATE, MEMBER_COUNT). | DEV-089 |  | DEV-089
TR-04 | DEV-089 | DEV-089 | Workbench | S40K9000004 | TR-03 | DB: ZBUG_USER_PROJEC + ZBUG_USERS extension — Create ZBUG_USER_PROJEC (10 fields). Add 4 new fields to ZBUG_USERS: EMAIL, FULL_NAME, DEPARTMENT, SKILL_LEVEL. | DEV-089 |  | DEV-089
TR-05 | DEV-089 | DEV-089 | Workbench | S40K9000005 | TR-04 | SE51: 4 new screens — Screen 0410 (Project Search, Normal), Screen 0370 (Status Transition Popup, Modal Dialog), Screen 0210 (Bug Search Input, Modal Dialog), Screen 0220 (Bug Search Results, Normal). Includes flow logic PBO/PAI. | DEV-089 |  | DEV-089
TR-06 | DEV-089 | DEV-089 | Workbench | S40K9000006 | TR-05 | SE41: GUI Statuses + Title Bars — Create STATUS_0410, STATUS_0370, STATUS_0210, STATUS_0220. Update STATUS_0200 (+SEARCH button). Create Title Bars T_0410/T_0370/T_0210/T_0220. | DEV-089 |  | DEV-089
TR-07 | DEV-089 | DEV-089 | Workbench | S40K9000007 | TR-06 | SE38: CODE v5.0 — All 6 includes: Z_BUG_WS_TOP, Z_BUG_WS_F00, Z_BUG_WS_PBO, Z_BUG_WS_PAI, Z_BUG_WS_F01, Z_BUG_WS_F02. Includes 10-state lifecycle, auto-assign, Screen 0370 popup, matrix logic, bug search, dashboard, 11 UAT bug fixes. | DEV-089 |  | DEV-089
TR-08 | DEV-089 | DEV-089 | Workbench | S40K9000008 | TR-07 | SE93: T-Code ZBUG_WS update — Change initial screen from 0400 to 0410. GUI status from STATUS_0400 to STATUS_0410. | DEV-089 |  | DEV-089
TR-09 | DEV-089 | DEV-089 | Workbench | S40K9000009 | TR-07 | SMW0: Template files — Upload 3 renamed templates: Bug_report.xlsx (ZBT_TMPL_01), fix_report.xlsx (ZBT_TMPL_02), confirm_report.xlsx (ZBT_TMPL_03). Object type: W3MIME / Binary Web Object. | DEV-089 |  | DEV-089
POST-IMPORT ACTIONS (Manual — Not in TR)
Step | Action | Tool | Account | When
M-01 | Activate all imported objects (activate queue) | SE80 / SE38 |  | DEV-089 | After TR-07 import
M-02 | Run data migration: UPDATE ZBUG_TRACKER SET STATUS = V WHERE STATUS = 6 | SE38 / SE16 |  | DEV-089 | After TR-07, before UAT Round 2
M-03 | Verify ZBUG_EVIDENCE table exists and is active | SE11 |  | DEV-089 | After TR-01 import
M-04 | Load test data: 30 mock users in ZBUG_USERS | SE16 |  | DEV-089 | Before UAT Round 2
M-05 | Assign test users to test projects in ZBUG_USER_PROJEC | SE16 |  | DEV-089 | Before UAT Round 2
M-06 | Smoke test: /nZBUG_WS -> Screen 0410 appears | SM50 |  | DEV-089 | After TR-08 import
UAT SIGN-OFF CHECKLIST
# | Checkpoint | Verified by | Date | Sign-Off
1 | All TRs (TR-01 to TR-09) successfully imported to UAT without errors | [7 empty] | DEV-089
2 | Manual steps M-01 to M-06 completed | [7 empty] | DEV-089
3 | Status migration executed: no STATUS=6 records remain | [7 empty] | DEV-089
4 | UAT Round 2 — all 46 cases PASS | [7 empty] | DEV-089, DEV-061, DEV-118
5 | 11 UAT Round 1 bugs verified FIXED | [7 empty] | DEV-089
6 | T-Code ZBUG_WS starts on Screen 0410 (Project Search) | [7 empty] | DEV-089
7 | Auto-assign works: New -> Assigned (Developer) | [7 empty] | DEV-061
8 | Auto-assign works: Fixed -> Final Testing (Tester) | [7 empty] | DEV-118
9 | Status transition matrix enforced for all 3 roles | [7 empty] | DEV-089, DEV-061, DEV-118
10 | Evidence upload required before Fixed (5) transition | [7 empty] | DEV-118
PRD Go-Live Approved | All above checkpoints signed off | [7 empty] | DEV-089 (Manager)