## Cover
UAT — User Acceptance Test
Z_BUG_WORKSPACE_MP — Bug Tracking System v5.0
Project Name | Z_BUG_WORKSPACE_MP — Bug Tracking System
Business Flow | Full system acceptance by key users
Test Level | UAT — User Acceptance Test
SAP System | S40
Client | 324
T-Code | ZBUG_WS
Version | 1.0
Date | 17/04/2026
Business Key Users | DEV-089 (Manager), DEV-061 (Developer), DEV-118 (Tester)
UAT Accounts
Account | Role | Password | Email
DEV-089 | Manager (M) | @Anhtuoi123 | TANTAISERVER2025@GMAIL.COM
DEV-061 | Developer (D) | @57Dt766 | HUGHNGUYEN1201@GMAIL.COM
DEV-118 | Tester (T) | Qwer123@ | NGUYENTANTAI.DEV@GMAIL.COM

## Histories
Change History — UAT
No. | Version | Description | Sheet | Modified Date | Modified by | Remarks
1 | 1.0 | Initial UAT plan — v5.0 | All | 17/04/2026 | DEV-089

## Test Scenario
UAT Test Scenarios A-H
Scenario UAT-A: Access and Navigation
No. | Step Name | Menu Path | T-Code | Scenario / Action | Exec | Pass/Fail | Notes
1 | Start the system | — | ZBUG_WS | Run /nZBUG_WS -> Project Search screen (0410) appears with 3 input fields | DEV-089
2 | List all projects | Screen 0410 | — | Execute with empty filters -> Project List (0400) shows all projects | DEV-089
3 | Enter Bug List | Screen 0400 | — | Double-click PRJ0000001 -> Bug List (0200) with Dashboard at top | DEV-089
4 | View bug detail | Screen 0200 | — | Select bug -> Display -> Screen 0300 with 6 tabs | DEV-089
5 | Navigate back | Screen 0300 | — | Back (F3) repeatedly: 0300->0200->0400->0410 | DEV-089
6 | Exit system | Screen 0410 | — | Back (F3) -> SAP menu | DEV-089
Scenario UAT-B: Project Search (Screen 0410)
No. | Step Name | Menu Path | T-Code | Scenario / Action | Exec | Pass/Fail | Notes
1 | Search by Project ID | Screen 0410 | — | Enter Project ID = PRJ0000001 -> Execute -> only that project shown | DEV-089
2 | Search by Manager | Screen 0410 | — | Enter Manager = DEV-089 -> Execute -> only DEV-089 projects | DEV-089
3 | Search by Status | Screen 0410 | — | Status = 2 (In Process) -> Execute -> only In Process projects | DEV-089
4 | F4 lookup | Screen 0410 | — | F4 on Project ID field -> popup lists all projects -> select fills field | DEV-089
Scenario UAT-C: Project Management
No. | Step Name | Menu Path | T-Code | Scenario / Action | Exec | Pass/Fail | Notes
1 | Create project | Screen 0400 -> Create Project | — | Fill name, manager, dates -> Save -> PROJECT_ID auto-generated | DEV-089
2 | Add Developer | Screen 0500 -> Add User | — | USER_ID=DEV-061, ROLE=D -> appears in table | DEV-089
3 | Add Tester | Screen 0500 -> Add User | — | USER_ID=DEV-118, ROLE=T -> appears in table | DEV-089
4 | Change project status | Screen 0500 | — | STATUS: 1(Opening) -> 2(In Process) -> Save | DEV-089
5 | Block Delete with bugs | Screen 0400 -> Delete | — | Project has open bugs -> error: cannot delete | DEV-089
6 | Developer cannot create project | Screen 0400 | — | DEV-061 clicks Create Project -> access denied | DEV-061
Scenario UAT-D: Bug Management
No. | Step Name | Menu Path | T-Code | Scenario / Action | Exec | Pass/Fail | Notes
1 | Create bug (Tester) | Screen 0200 -> Create | ZBUG_WS | Fill TITLE, MODULE=FI, PRIORITY=H, SEVERITY=V -> Save | DEV-118
2 | PROJECT_ID pre-filled | Screen 0300 | — | PROJECT_ID = current project, field is locked | DEV-118
3 | Auto-assign Dev | After create | — | If DEV-061 is FI Dev with workload<5: STATUS=Assigned, DEV_ID=DEV-061 | DEV-118
4 | Edit bug (Manager) | Screen 0200 -> Change | — | Change TITLE, PRIORITY -> Save -> updated | DEV-089
5 | FNC fields locked for Dev | Screen 0300 (DEV-061) | — | PRIORITY/SEVERITY/BUG_TYPE fields are input-disabled | DEV-061
6 | Delete bug | Screen 0200 -> Delete | — | Confirm -> bug gone from list; IS_DEL=X in DB | DEV-089
Scenario UAT-E: Status Transitions (Popup 0370)
No. | Step Name | Menu Path | T-Code | Scenario / Action | Exec | Pass/Fail | Notes
1 | Open status popup | Screen 0300 -> Change Status | — | Popup 0370 shows Bug ID, Title, Reporter, Current Status + dropdown | DEV-089
2 | New -> Assigned | Popup 0370 | — | Manager selects status=2, DEV_ID=DEV-061 -> Confirm | DEV-089
3 | Assigned -> In Progress | Popup 0370 | — | DEV-061 selects status=3 -> Confirm | DEV-061
4 | Upload fix evidence | Tab Evidence -> Upload Fix | — | fix_report.xlsx uploaded | DEV-061
5 | In Progress -> Fixed | Popup 0370 | — | DEV-061 selects status=5 -> auto-assign tester -> STATUS=6 | DEV-061
6 | Final Testing -> Resolved | Popup 0370 | — | DEV-118 selects V, TRANS_NOTE=All verified -> Confirm | DEV-118
7 | Cancel popup | Popup 0370 | — | Cancel (F12) -> popup closes, status unchanged | DEV-089
8 | Invalid transition blocked | Popup 0370 | — | Tester tries New->Resolved directly -> not in dropdown | DEV-118
Scenario UAT-F: Evidence Handling
No. | Step Name | Menu Path | T-Code | Scenario / Action | Exec | Pass/Fail | Notes
1 | Download Bug Report template | Screen 0200 -> Download Testcase | — | Bug_report.xlsx downloaded and auto-opens | DEV-089
2 | Upload Bug Report | Tab Evidence -> Upload Report | — | Bug_report.xlsx uploaded -> row in evidence table | DEV-118
3 | Upload Fix evidence | Tab Evidence -> Upload Fix | — | fix_report.xlsx uploaded | DEV-061
4 | Upload Confirm evidence | Tab Evidence -> Upload Evidence | — | confirm_report.xlsx uploaded | DEV-118
5 | Download evidence | Select row -> Download Evidence | — | File saved to local PC with original filename | DEV-089
6 | Evidence required for Fixed | Popup 0370 -> select 5 (no evidence) | — | Error: evidence required | DEV-061
Scenario UAT-G: Dashboard and Bug Search
No. | Step Name | Menu Path | T-Code | Scenario / Action | Exec | Pass/Fail | Notes
1 | Dashboard visible | Screen 0200 | — | Dashboard header shows: Total, New, Assigned, InProgress, Fixed, FinalTesting, Resolved, Waiting | DEV-089
2 | Counts correct | Screen 0200 | — | Count bugs manually -> matches Dashboard | DEV-089
3 | Dashboard refreshes | After status change -> Refresh | — | Counts update | DEV-089
4 | Open Bug Search | Screen 0200 -> SEARCH | — | Popup 0210 appears | DEV-089
5 | Search by title | Popup 0210 -> Title=FI -> Execute | — | Screen 0220 shows only FI-related bugs | DEV-089
6 | Search by status | Popup 0210 -> Status=3 -> Execute | — | Only In Progress bugs shown | DEV-089
Scenario UAT-H: Email, My Bugs, Templates
No. | Step Name | Menu Path | T-Code | Scenario / Action | Exec | Pass/Fail | Notes
1 | Send email | Screen 0300 -> SENDMAIL | — | Message: Email sent -> check SOST | DEV-089
2 | My Bugs — Developer | Screen 0400 -> My Bugs | — | Only bugs with DEV_ID=DEV-061 listed | DEV-061
3 | My Bugs — Tester | Screen 0400 -> My Bugs | — | Bugs where TESTER_ID or VERIFY_TESTER_ID = DEV-118 | DEV-118
4 | Upload Project Excel | Screen 0400 -> Upload | — | Upload valid Excel -> projects created | DEV-089

## Test Cases
UAT Test Cases — Detailed
UAT-TC-01: Full Happy Path
NO. | Step | Test Case ID | Test Data | Expected Result | Created by | Date
1 | Create bug | TC-01.1 | TITLE=FI tax error, MODULE=FI, PRIORITY=H | BUG auto-generated, STATUS=Assigned | DEV-118
2 | Accept + InProgress | TC-01.2 | DEV-061 opens popup -> status=3 | STATUS=In Progress | DEV-061
3 | Fix + evidence | TC-01.3 | fix_report.xlsx -> status=5 | STATUS=Final Testing, Tester assigned | DEV-061
4 | Resolve | TC-01.4 | DEV-118, TRANS_NOTE=OK -> V | STATUS=Resolved | DEV-118
UAT-TC-02: Negative Cases
NO. | Step | Test Case ID | Test Data | Expected Result | Created by | Date
1 | Fixed without evidence | TC-02.1 | Status change 3->5, no evidence | Error: evidence required | DEV-061
2 | Resolved without note | TC-02.2 | Status change 6->V, TRANS_NOTE empty | Error: note required | DEV-118
3 | Dev create bug | TC-02.3 | DEV-061 -> Create in Bug List | Access denied | DEV-061
4 | Project Done with open bugs | TC-02.4 | STATUS=3 while bugs open | Error: X open bug(s) | DEV-089

## Test Result
UAT Test Result — Sign-Off
Scenario | Total Cases | Pass | Fail | Pass Rate | Sign-Off (User) | Date
A. Access and Navigation | 6 |  |  |  | DEV-089
B. Project Search | 4 |  |  |  | DEV-089
C. Project Management | 6 |  |  |  | DEV-089
D. Bug Management | 6 |  |  |  | DEV-089/118
E. Status Transitions | 8 |  |  |  | DEV-089/061/118
F. Evidence | 6 |  |  |  | DEV-089/061/118
G. Dashboard and Search | 6 |  |  |  | DEV-089
H. Email, My Bugs | 4 |  |  |  | DEV-089/061/118
Total | 46
UAT PASS criteria: All 46 cases Pass (0 Fail). Any Fail must be logged in Test_And_Fix_Bug tracker, fixed, and retested before go-live approval.